BUSINESSLOGIC PLATFORM

Evolution Plan

From Monolith to State-of-the-Art Modular Platform

Version 1.0  —  March 20, 2026

Confidential — Coignite ApS

# 1. Vision & Guiding Principles

This document defines the complete evolution plan to transform the BusinessLogic platform from its current partially-embedded architecture into a fully modular, independently-scalable service mesh. The end state is a platform where every compute-intensive concern runs as an independent service, Directus acts purely as back-office, and public APIs follow a single, proven pattern with security controls at every level.

## 1.1 Target State (One Sentence)

Five independent services (CMS, Formula API, AI API, Flow Engine, Gateway) communicating over a private network, each horizontally scalable, crash-isolated, and deployable independently via Coolify on Hetzner bare metal.

## 1.2 Guiding Principles

| Principle | Meaning | Example |
| --- | --- | --- |
| Single Responsibility | Each service owns exactly one domain | AI API owns chat, KB search, embedding — not Directus |
| Proven Patterns First | Reuse what works before inventing | AI API mirrors formula-api’s worker pool, auth, rate limiting |
| Rust for Compute, Node/Go for I/O | Use each language where it excels | Rust flow engine for DAG execution, Fastify for HTTP API surface |
| Gateway for Public, Direct for Private | Public traffic through gateway, internal traffic direct | Client → Gateway → AI API vs Flow Worker → AI API (direct) |
| Budget Enforcement Everywhere | Every AI call has cost controls | 5-layer budget system from flow engine, applied to AI API |
| Observable by Default | Every service emits traces, metrics, health | OpenTelemetry from day one in new services |

# 2. Target Architecture

## 2.1 Service Topology

| Service | Technology | Purpose | Public API | Scaling Unit |
| --- | --- | --- | --- | --- |
| bl-gateway | Go | API gateway, auth, rate limiting, routing | Yes — all public traffic | Stateless, per-CPU |
| bl-cms | Node.js | Directus: back-office, admin UI, data management | Admin only | Single instance |
| bl-formula-api | Node.js + Rust | Formula evaluation, calculators, MCP | Via gateway | Worker pool, hash ring |
| bl-ai-api | Node.js | AI chat, KB search, answer gen, embeddings | Via gateway | Worker pool |
| bl-flow | Rust | DAG workflow execution, AI orchestration | Via gateway (webhooks) | Consumer groups |

## 2.2 Communication Flow

Public path: Client → Cloudflare → bl-gateway (auth + rate limit + route) → target service → response

Internal path: Service → Service (direct HTTP/gRPC over private 10.0.0.0/16, no gateway)

Async path: Service → Redis Streams → Consumer (bl-flow workers, bl-ai-api indexing workers)

## 2.3 Data Layer (Shared)

| Store | Technology | Purpose | Accessed By |
| --- | --- | --- | --- |
| Primary DB | PostgreSQL 16 + pgvector | All persistent data, vectors, flow definitions | All services (scoped schemas) |
| Cache / Queue | Redis 7 (Sentinel) | Cache, rate limits, job queues, streams, pubsub | All services |
| Object Storage | Hetzner Object Storage (S3) | Large flow outputs, KB documents, backups | bl-ai-api, bl-flow |

# 3. Service Design: bl-gateway

## 3.1 Why a Gateway (and Why Go)

Currently, Traefik does basic reverse proxying but has no application-level intelligence. Every service implements its own auth validation, rate limiting, and CORS handling. A dedicated API gateway centralises these cross-cutting concerns, reduces duplication, and provides a single point for API key management and analytics.

Why Go: The gateway is pure I/O (parse request, check Redis, proxy to backend). Go excels here: goroutines handle 100K+ concurrent connections with sub-millisecond overhead, the binary is ~10MB (vs ~150MB for Node.js), startup is <100ms, and the ecosystem (net/http, crypto/subtle) is battle-tested for proxy workloads. Go is also significantly easier to hire for than Rust, and the gateway needs fast iteration as business requirements change.

## 3.2 Responsibilities

| Concern | Implementation | Details |
| --- | --- | --- |
| API Key Validation | Redis LRU cache + PostgreSQL fallback | Key format: bl_{accountId}_{env}_{random32}. Cache valid keys 10min, invalid 1min. Timing-safe comparison. |
| Rate Limiting | Redis sliding window (Lua script) | Per-key RPS + monthly quota. Same proven pattern as formula-api. 429 + Retry-After on exceed. |
| Route Resolution | Static config + service discovery | Routes: /v1/ai/* → bl-ai-api, /v1/calc/* → bl-formula-api, /v1/flows/* → bl-flow, /admin/* → bl-cms |
| CORS | Per-key origin allowlist | Mirrors formula-api’s per-calculator allowlist, now per-API-key |
| IP Allowlist | Per-key IP/CIDR check | net.BlockList equivalent in Go (netip.Prefix). O(1) lookup. |
| Request Logging | Structured JSON (zerolog) | Request ID, account ID, latency, status, service — shipped to Loki |
| Health Aggregation | Checks all backends | /health returns composite status of all downstream services |
| TLS Termination | Cloudflare (external), Go TLS (internal) | mTLS between gateway and backends on private network |

## 3.3 API Key Model

Replaces the current per-calculator token system with a unified account-level API key that works across all services:

| Field | Type | Example | Purpose |
| --- | --- | --- | --- |
| key | string | bl_acc123_live_a1b2c3d4e5f6... | Public identifier (sent in X-API-Key header) |
| key_hash | string | sha256(key) | Stored in DB (never store raw key) |
| account_id | uuid | acc_123 | Links to account for billing/quotas |
| environment | enum | live / test / dev | Separate quotas per environment |
| permissions | jsonb | {"ai": true, "calc": true, "flow": false} | Service-level access control |
| allowed_ips | text[] | ["203.0.113.0/24"] | IP allowlist (null = allow all) |
| allowed_origins | text[] | ["https://app.example.com"] | CORS origins (null = allow all) |
| rate_limit_rps | int | 100 | Override account default |
| monthly_quota | int | 1000000 | Override account default |
| expires_at | timestamptz | null | Optional expiration |

# 4. Service Design: bl-ai-api

## 4.1 Overview

bl-ai-api is a standalone Fastify service that owns all AI capabilities: chat with tool use, knowledge base ingestion/search/answer, and embedding generation. It follows the proven formula-api architecture pattern: Fastify HTTP surface, worker thread pool for compute, backpressure management, and two-layer caching.

Why Node.js (not Rust/Go): The AI API is I/O-bound, not compute-bound. The bottleneck is waiting for Anthropic API responses (50-2000ms) and PostgreSQL queries (1-10ms). Node.js’s async I/O handles this efficiently. The Anthropic SDK is TypeScript-native. Streaming SSE is trivial in Fastify. The team has deep Node.js expertise. Rust/Go would add complexity without meaningful performance benefit for I/O-bound work.

Where Rust helps: Local embedding inference via the flow engine’s fastembed ONNX node ($0 cost, 5-10ms/doc). bl-ai-api delegates embedding to bl-flow or uses businesslogic-excel’s napi-rs pattern to call a Rust ONNX wrapper directly.

## 4.2 API Surface (Public via Gateway)

| Method | Endpoint | Auth | Purpose |
| --- | --- | --- | --- |
| POST | /v1/ai/chat | API Key + AI permission | AI chat with streaming (SSE). Tool loop up to N rounds. |
| POST | /v1/ai/chat/sync | API Key + AI permission | Non-streaming chat. Returns complete response. |
| POST | /v1/ai/conversations | API Key + AI permission | Create a new conversation context |
| GET | /v1/ai/conversations/:id | API Key + AI permission | Retrieve conversation history |
| DELETE | /v1/ai/conversations/:id | API Key + AI permission | Delete conversation |
| POST | /v1/ai/kb/search | API Key + AI permission | Hybrid search (vector + FTS + RRF). Returns ranked chunks. |
| POST | /v1/ai/kb/ask | API Key + AI permission | Search + LLM answer generation with citations |
| POST | /v1/ai/kb/ingest | API Key + AI permission | Upload document for KB ingestion (async, returns job ID) |
| GET | /v1/ai/kb/ingest/:jobId | API Key + AI permission | Check ingestion job status |
| POST | /v1/ai/embeddings | API Key + AI permission | Generate embeddings for input texts |
| GET | /v1/ai/usage | API Key | Token usage and cost report for account |
| GET | /v1/ai/models | API Key | List available models and their capabilities |
| POST | /v1/ai/mcp/:knowledgeBaseId | API Key + AI permission | MCP endpoint for KB (JSON-RPC 2.0, same pattern as formula-api) |

## 4.3 Architecture Internals

### 4.3.1 Worker Thread Pool (from formula-api)

Port the engine-pool.js pattern from formula-api for LLM calls and embedding generation:

| Component | Purpose | Configuration |
| --- | --- | --- |
| Chat Workers | Handle LLM streaming conversations | CHAT_POOL_SIZE (default: 4). Each worker manages Anthropic SDK connection. |
| Embedding Workers | Process embedding requests (local ONNX or API) | EMBED_POOL_SIZE (default: 2). Batch up to 256 texts per call. |
| Ingestion Workers | Process KB document ingestion queue | INGEST_POOL_SIZE (default: 2). Consume from BullMQ queue. |
| Dispatch | Round-robin with pending map | Same atomic counter + Promise correlation as formula-api |
| Backpressure | MAX_QUEUE_DEPTH per pool | 503 rejection when queue full. Configurable per pool. |
| Crash Recovery | Worker exit → auto-respawn | Pending requests rejected with 503. New worker spawned immediately. |

### 4.3.2 KB Ingestion Pipeline (BullMQ)

Replace the current setTimeout(0) fire-and-forget with a proper job queue:

- Document uploaded via /v1/ai/kb/ingest → stored in S3/local

- Job enqueued to BullMQ with priority (re-index = low, new doc = high)

- Ingestion worker dequeues: parse (PDF/DOCX/XLSX/TXT) → section-aware chunking

- Version hash check: skip unchanged chunks (SHA-256 of content)

- Embed chunks: local ONNX (default) or OpenAI API (configurable per account)

- Store in kb_chunks with pgvector HNSW index

- Job status queryable via /v1/ai/kb/ingest/:jobId (queued/processing/done/failed)

### 4.3.3 Budget Enforcement (5-Layer, from Flow Engine)

Port the flow engine’s proven budget system to bl-ai-api:

| Layer | Scope | Storage | Default | Action on Exceed |
| --- | --- | --- | --- | --- |
| 1. Per-request | Single chat/ask call | Response header | Informational | Log cost, return in X-AI-Cost header |
| 2. Per-conversation | Cumulative for conversation | PostgreSQL | $1.00 | Stop tool loop, return partial answer |
| 3. Daily per-account | All requests today | Redis (25h TTL) | $10.00 | 429 + Retry-After: seconds-until-midnight |
| 4. Monthly per-account | All requests this month | PostgreSQL | $100.00 | 429 + upgrade-plan message |
| 5. Global platform | All accounts combined | Redis (25h TTL) | $500.00 | 503 + circuit breaker for 5 minutes |

### 4.3.4 Two-Layer Caching

| Layer | Technology | TTL | Use Case |
| --- | --- | --- | --- |
| L1: In-process LRU | lru-cache (npm) | 5 min | Repeated identical queries within instance. O(1) lookup, zero network. |
| L2: Redis | Redis 7 | 1 hour | Cross-instance cache. KB answers, embedding results. |

Cache key: SHA-256(account_id + query + model + temperature + kb_id). Cache invalidated on KB re-index.

# 5. Service Design: bl-flow (Evolution)

## 5.1 Current State

The flow engine is already the most architecturally advanced component. Phases 1-5 are complete: DAG execution, AI nodes, WASM plugins, access control, triggers. The evolution focuses on making it the strategic AI orchestration layer.

## 5.2 Evolution Steps

| Step | What | Why | Effort |
| --- | --- | --- | --- |
| 5.2.1 | KB Ingestion as Flow | Visual pipeline, local embeddings ($0), observability, retry per step | 2-3 weeks |
| 5.2.2 | KB Search as Flow | Budget enforcement, reranking as node, A/B testing search strategies | 1-2 weeks |
| 5.2.3 | AI Chat Tool Execution as Flow | Every tool call gets budget control, error handling, audit trail | 2-3 weeks |
| 5.2.4 | Phase 6: Visual Editor | Non-developer flow creation, real-time execution monitor | 4-6 weeks |
| 5.2.5 | Phase 7: Hardening | OpenTelemetry, load testing, security audit, chaos testing | 3-4 weeks |
| 5.2.6 | Composite Flows | Chain: user query → KB search → calculator → LLM synthesis | 2-3 weeks |

## 5.3 Flow-as-AI-Backend Pattern

Instead of bl-ai-api implementing AI logic directly, it delegates to flows for complex operations:

- Simple: Direct LLM call (bl-ai-api handles internally, no flow needed)

- Medium: KB search + answer → bl-ai-api triggers a pre-built flow via Redis Streams

- Complex: Multi-step research (search KB + run calculator + synthesise) → flow with parallel branches

- Custom: Customer-defined flows exposed as AI tools (visual builder)

Key benefit: The flow engine’s budget system, error handling, checkpointing, and observability apply automatically to every AI operation. No duplication in bl-ai-api.

# 6. bl-gateway: Go Implementation Details

## 6.1 Architecture

| Package | Responsibility | Key Dependencies |
| --- | --- | --- |
| main.go | HTTP server, graceful shutdown, config loading | net/http, envconfig |
| handler/proxy.go | Reverse proxy with circuit breaker | httputil.ReverseProxy, per-backend health |
| middleware/auth.go | API key extraction, validation, caching | crypto/subtle, Redis client |
| middleware/ratelimit.go | Sliding window rate limiting | Redis Lua scripts (same as formula-api) |
| middleware/cors.go | Per-key origin/IP allowlist | netip.Prefix for CIDR |
| middleware/logging.go | Structured request logging | zerolog, request ID propagation |
| service/keys.go | API key CRUD (internal API for CMS) | PostgreSQL driver |
| service/health.go | Backend health aggregation | Periodic HTTP checks, composite /health |
| service/metrics.go | Prometheus metrics export | promhttp, request counters/histograms |

## 6.2 Request Flow

- Cloudflare terminates TLS, forwards to bl-gateway (port 443 internal)

- Middleware chain: RequestID → Logger → CORS → Auth → RateLimit → Route

- Auth: Extract X-API-Key header → SHA-256 hash → Redis LRU lookup → PostgreSQL fallback

- RateLimit: Redis INCR with Lua (same script as formula-api, ported to Go client)

- Route: prefix match → ReverseProxy to backend (with circuit breaker)

- Backend responds → gateway adds X-Request-ID, X-RateLimit-* headers → client

## 6.3 Resource Requirements

| Metric | Value | Notes |
| --- | --- | --- |
| Binary size | ~12 MB | Single static binary, no runtime dependencies |
| Memory | ~50 MB base + ~1 KB/connection | 10K connections ≈ 60 MB total |
| CPU | 0.5 vCPU per 10K RPS | Goroutine-per-request, near-zero scheduling overhead |
| Startup time | <100ms | Config + Redis connection + health check |
| Latency overhead | <1ms p99 | Parse headers + Redis lookup + proxy |

# 7. Technology Analysis: Rust vs Go vs Node.js

## 7.1 Decision Matrix

| Workload | Best Choice | Runner-Up | Rationale |
| --- | --- | --- | --- |
| API Gateway (I/O + auth + rate limit) | Go | Node.js | 100K+ concurrent connections, sub-ms proxy latency, small binary, easy hiring |
| Formula compute engine | Rust | Go | Zero-GC, 8.3x memory efficiency, napi-rs integration. Already built. |
| Flow DAG execution | Rust | Go | Sub-µs dispatch, Tokio async, zero-copy. Already built. |
| AI API (HTTP + streaming) | Node.js | Go | I/O-bound, Anthropic SDK is TS-native, SSE trivial, team expertise |
| Embedding inference (local) | Rust | Go | ONNX Runtime bindings, zero-copy tensors. Already built in flow engine. |
| LLM API calls | Node.js | Go | Waiting for external API. No CPU work. SDK ecosystem. |
| KB ingestion pipeline | Node.js | Rust | I/O-bound (parse docs, call embed, store). BullMQ ecosystem. |
| Admin back-office | Node.js | — | Directus. No change needed. |

## 7.2 Go: When and Why

Use Go for the API gateway only. Go’s strengths are exactly what a gateway needs: massive concurrency via goroutines (M:N scheduling with <4KB per goroutine), excellent standard library for HTTP proxying, fast TLS, simple deployment (single binary), and fast compilation for iteration. Go is not appropriate for compute-intensive work (no zero-cost abstractions, GC pauses under memory pressure) or for the AI API (no Anthropic SDK, would need to maintain custom client).

## 7.3 Rust: When and Why

Use Rust for compute engines and real-time execution. The platform already has two production Rust codebases (businesslogic-excel, businesslogic-flow) proving the pattern. Rust excels where the formula engine and flow engine operate: zero-GC execution, arena allocation, SIMD vectorisation, and predictable latency. New Rust services should follow the existing patterns: napi-rs for Node.js integration, Axum for HTTP services, Tokio for async runtime.

## 7.4 Node.js: When and Why

Use Node.js for I/O-bound API services. The AI API is waiting for external services 99% of the time (Anthropic API: 50-2000ms, PostgreSQL: 1-10ms, Redis: <1ms). Node.js handles this efficiently with its event loop. The Fastify framework delivers 80K+ RPS on a single core for simple I/O. The team has deep expertise, the Anthropic SDK is TypeScript-native, and the formula-api provides a complete reference implementation for the worker pool, auth, caching, and rate limiting patterns.

# 8. Hetzner / Coolify Deployment Plan

## 8.1 Server Topology Evolution

Current: 3 servers (€31/mo). Target: 5 servers (€83/mo) for 10x capacity.

| Server | Spec | Monthly | Services | Rationale |
| --- | --- | --- | --- | --- |
| S1: Gateway | CX22 (2 vCPU, 4 GB) | €6 | bl-gateway, Coolify agent, Traefik | Gateway is lightweight (50 MB). Traefik for internal routing. |
| S2: CMS | CX22 (2 vCPU, 4 GB) | €6 | bl-cms (Directus) | Dedicated to back-office. No longer shares with compute. |
| S3: Data | CX32 (4 vCPU, 8 GB) | €14 | PostgreSQL 16 + pgvector, Redis 7 Sentinel | Upgraded: 8GB for pgvector HNSW indexes + Redis cache |
| S4: AI Compute | CX32 (4 vCPU, 8 GB) | €14 | bl-ai-api (3 instances), embedding workers | Dedicated AI server. 4 vCPU = 4 chat workers + 2 embed workers |
| S5: Compute | CPX31 (4 vCPU, 8 GB) | €17 | bl-formula-api, bl-flow trigger, bl-flow workers | Same as current S3. Formula + Flow compute. |

Total: ~€57/month (current €31/month + €26 for dedicated AI and upgraded data server). Supports 10x current capacity.

## 8.2 Scaling Tiers

| Tier | Accounts | Monthly Cost | Changes from Previous Tier |
| --- | --- | --- | --- |
| Starter | 1-100 | €57/mo | Base 5-server setup as described above |
| Growth | 100-500 | €120/mo | S4 → CX42 (8 vCPU, 16 GB). Add S6 as second formula-api node. |
| Scale | 500-2000 | €250/mo | S3 → CX52 (16 vCPU, 32 GB). S4 → 2x CX32. S5 → 2x CX32. Add S7 for Redis Sentinel standby. |
| Enterprise | 2000+ | €500+/mo | Dedicated hosts, multiple regions, read replicas, managed Redis. Consider Hetzner Dedicated. |

## 8.3 Coolify Service Configuration

Each service deployed as a Coolify “Service” with Docker Compose:

| Service | Image | Resources | Health Check | Replicas |
| --- | --- | --- | --- | --- |
| bl-gateway | bl-gateway:${TAG} | 0.5 vCPU, 256 MB | GET /health (2s interval) | 1 (S1) |
| bl-cms | bl-cms:${TAG} | 1 vCPU, 2 GB | GET /server/ping (10s) | 1 (S2) |
| bl-ai-api | bl-ai-api:${TAG} | 1 vCPU, 2 GB each | GET /ping (5s) | 2-3 (S4) |
| bl-formula-api | bl-formula-api:${TAG} | 2 vCPU, 2 GB | GET /ping (5s) | 1-2 (S5) |
| bl-flow-trigger | bl-flow:trigger | 0.5 vCPU, 512 MB | GET /health (5s) | 1 (S5) |
| bl-flow-worker | bl-flow:worker | 1.5 vCPU, 2 GB each | — (consumer group) | 2-4 (S5) |

## 8.4 Networking

| Layer | Configuration | Purpose |
| --- | --- | --- |
| Hetzner Private Network | 10.0.0.0/16, all servers joined | Zero-cost internal traffic, no public exposure for S3-S5 |
| Hetzner Firewall | S1: 80,443 inbound. S2-S5: deny all public | Only gateway accepts public traffic |
| Coolify Docker Network | Per-server bridge, cross-server via private IPs | Container-to-container communication |
| Cloudflare | DNS + WAF + CDN for bl-gateway domain | DDoS protection, geo-routing, edge caching |
| Service Discovery | Static IPs + environment variables | Simple, predictable (no Consul/etcd needed at this scale) |

## 8.5 Zero-Downtime Deployment

Coolify supports rolling deployments with health check gates:

- Push image to registry (Coolify built-in or GitHub Container Registry)

- Coolify pulls new image, starts new container alongside old

- Health check passes on new container (GET /ping returns 200)

- Coolify drains connections from old container (30s grace period)

- Old container removed. New container takes over.

- If health check fails: automatic rollback to previous image

bl-formula-api special case: Calculators are stateful (in-memory). On deployment, the new instance rebuilds active calculators from Redis recipes. The hash ring rebalances automatically. Client-facing latency spike: ~50-100ms per affected calculator (one-time rebuild).

# 9. Phased Implementation Plan

## Phase 0: Foundation Fixes (Weeks 1-2)

Goal: Fix critical issues in current architecture with zero architectural change.

| Task | Effort | Impact | Details |
| --- | --- | --- | --- |
| Add HNSW index to pgvector | 0.5 day | 10x KB search speed at scale | Single SQL migration: CREATE INDEX ... USING hnsw (embedding vector_cosine_ops) WITH (m=16, ef_construction=200) |
| Add BullMQ for KB indexing | 3-5 days | Reliable ingestion with retry | Replace setTimeout(0). Job states: queued/active/done/failed. Dashboard via Bull Board. |
| Document version hashing | 2 days | 80-90% re-index cost reduction | SHA-256 of chunk content. Skip unchanged chunks. Store hash in kb_chunks. |
| Enable reranking for paid plans | 1 day | Improved search precision | Cohere reranker already implemented. Enable by default for non-free tiers. |
| Add request ID propagation | 1 day | Debugging across services | X-Request-ID header generated at edge, forwarded to all services. |

## Phase 1: bl-ai-api Extraction (Weeks 3-6)

Goal: Extract AI features from Directus into standalone service.

| Week | Tasks | Deliverables |
| --- | --- | --- |
| 3 | Scaffold bl-ai-api (Fastify). Port chat endpoint with SSE streaming. Port conversation management. | AI chat working via standalone service |
| 3-4 | Port all 13 tools. Port KB search/ask. Port cost tracking. | Feature parity with Directus extension |
| 4 | Implement worker thread pool (port from formula-api). Add backpressure. | Non-blocking concurrent chat sessions |
| 5 | Port KB ingestion to BullMQ workers. Add version hashing. Add job status API. | Reliable async ingestion pipeline |
| 5-6 | Implement 5-layer budget system (port from flow engine). Add two-layer cache. | Cost control + performance |
| 6 | Integration testing. Update Directus to proxy AI requests to bl-ai-api. | Directus delegates, bl-ai-api serves |

## Phase 2: bl-gateway (Weeks 7-10)

Goal: Centralise auth, rate limiting, and routing in a Go gateway.

| Week | Tasks | Deliverables |
| --- | --- | --- |
| 7 | Scaffold bl-gateway in Go. Implement reverse proxy with health checks. | Basic proxying to all backends |
| 7-8 | Implement API key model (PostgreSQL + Redis cache). Port rate limiting (Lua scripts). | Unified auth across all services |
| 8-9 | Implement per-key CORS, IP allowlist. Add request logging (zerolog + Loki). | Full security controls per key |
| 9 | MCP routing: /v1/mcp/* routes to formula-api or ai-api MCP endpoints. | Unified MCP surface through gateway |
| 10 | Load testing (k6). Circuit breaker tuning. Documentation. | Production-ready gateway |
| 10 | Migrate formula-api public traffic through gateway. Deprecate direct access. | First service behind gateway |

## Phase 3: Public AI API (Weeks 11-14)

Goal: Expose AI capabilities as a public API with the same security model as calculators.

| Week | Tasks | Deliverables |
| --- | --- | --- |
| 11 | Define OpenAPI spec for /v1/ai/*. Implement API key → account resolution. | API contract defined |
| 11-12 | Public chat endpoint (/v1/ai/chat). SSE streaming through gateway. Tool scoping per API key. | Public AI chat API |
| 12-13 | Public KB endpoints (/v1/ai/kb/search, /ask, /ingest). Per-key KB scoping. | Public KB API |
| 13 | MCP endpoint for KB (/v1/ai/mcp/:kbId). Same JSON-RPC 2.0 pattern as calculators. | AI tools in MCP clients |
| 13-14 | Account-level MCP (/v1/mcp/account/:id). Single endpoint for all tools (calc + AI). | Unified MCP experience |
| 14 | SDK (TypeScript). Quick-start documentation. Rate limit headers. Usage dashboard. | Developer experience |

## Phase 4: Flow Engine as AI Backend (Weeks 15-20)

Goal: Migrate complex AI operations to flow-based execution.

| Week | Tasks | Deliverables |
| --- | --- | --- |
| 15-16 | KB ingestion as flow: parse → chunk → embed (local ONNX) → store. Visual pipeline. | Zero-cost embeddings, observable pipeline |
| 17 | KB search as flow: embed_query → vector_search → rerank → format. Budget per search. | Budget-controlled search |
| 18-19 | AI chat tool execution as flow: each tool call triggers a micro-flow with error handling. | Auditable, budget-controlled tool calls |
| 19-20 | Composite flows: user query → KB + calculator + LLM synthesis. Flow templates. | Multi-step AI reasoning |
| 20 | Phase 6 visual editor integration: non-developers can create AI flows. | Self-service AI pipeline building |

## Phase 5: Hardening & Observability (Weeks 21-24)

Goal: Production hardening, observability, and operational excellence.

| Week | Tasks | Deliverables |
| --- | --- | --- |
| 21-22 | OpenTelemetry across all services: traces, metrics, logs. Grafana dashboards. | End-to-end observability |
| 22-23 | Load testing: k6 scenarios for each service. Identify and fix bottlenecks. | Performance baselines and SLAs |
| 23 | Security audit: penetration testing, dependency scanning, secret rotation. | Security certification |
| 23-24 | Chaos testing: kill services, network partitions, Redis failures. Verify recovery. | Resilience validation |
| 24 | Runbook documentation. On-call procedures. SLA definitions. | Operational readiness |

# 10. Directus: Back-Office Only

## 10.1 What Stays in Directus

| Responsibility | Why It Stays | Changes Needed |
| --- | --- | --- |
| Admin UI (Vue 3) | Excellent CRUD interface, role-based access | Add proxy routes to bl-ai-api for AI assistant module |
| User/account management | Core CMS data model | None — gateway validates keys, CMS manages accounts |
| Calculator definition CRUD | Content management is Directus’s purpose | API calls to formula-api for execution (already working) |
| KB document management | File uploads, metadata, access control | Ingestion delegated to bl-ai-api via API call |
| Flow definition CRUD | Visual editor renders in Directus module | Flow execution delegated to bl-flow |
| Billing/subscription management | Business data | None — account limits used by gateway |
| API key management UI | Admin creates/rotates keys | New extension: API Key Manager (CRUD + analytics) |

## 10.2 What Moves Out of Directus

| Feature | Moves To | Timeline | Migration Strategy |
| --- | --- | --- | --- |
| AI chat endpoint | bl-ai-api | Phase 1 (Week 3-6) | Directus proxies to bl-ai-api. Frontend unchanged. |
| KB search/ask | bl-ai-api | Phase 1 (Week 3-6) | Same proxy pattern. KB data stays in shared PostgreSQL. |
| KB ingestion workers | bl-ai-api | Phase 1 (Week 5) | BullMQ workers in bl-ai-api. Directus triggers via API. |
| Embedding generation | bl-ai-api (local ONNX) | Phase 4 (Week 15) | Replace OpenAI calls with local inference. |
| Rate limiting (AI) | bl-gateway | Phase 2 (Week 7-10) | Gateway handles all rate limiting. Remove from Directus. |
| Public API auth | bl-gateway | Phase 2 (Week 7-10) | API keys managed in CMS, validated in gateway. |

## 10.3 Directus Resource Requirements (After Migration)

With compute offloaded, Directus requires significantly fewer resources:

| Metric | Before (with AI) | After (back-office only) | Savings |
| --- | --- | --- | --- |
| Memory | ~1.5 GB (AI + KB + CMS) | ~512 MB (CMS only) | 67% |
| CPU usage (peak) | 80% (LLM streaming blocks event loop) | 20% (CRUD + admin UI) | 75% |
| Crash risk | Medium (AI errors can crash Directus) | Low (only CMS operations) | Significant |
| Deploy frequency | High (AI changes require restart) | Low (CMS changes are rare) | Less disruption |

# 11. Database Schema Evolution

## 11.1 New Tables

| Table | Owner Service | Purpose | Key Columns |
| --- | --- | --- | --- |
| api_keys | bl-gateway (via CMS) | API key storage | key_hash, account_id, env, permissions, allowed_ips, allowed_origins, rate_limit_rps, monthly_quota |
| ai_conversations | bl-ai-api | Conversation state | id, account_id, model, messages (jsonb), created_at, total_cost_usd |
| ai_token_usage | bl-ai-api | Per-request cost log | id, account_id, conversation_id, model, input_tokens, output_tokens, cost_usd, timestamp |
| ai_budgets | bl-ai-api | Monthly budget tracking | account_id, month, total_cost_usd, budget_limit_usd |
| kb_ingest_jobs | bl-ai-api | Ingestion job tracking | id, account_id, kb_id, status, progress_pct, error, started_at, completed_at |

## 11.2 Schema Changes

| Table | Change | Reason |
| --- | --- | --- |
| kb_chunks | ADD INDEX USING hnsw (embedding vector_cosine_ops) | O(log n) vector search instead of O(n) scan |
| kb_chunks | ADD COLUMN content_hash TEXT | Skip re-embedding unchanged chunks |
| kb_chunks | ADD COLUMN embedding_model TEXT DEFAULT 'text-embedding-3-small' | Track which model generated each embedding |
| calculators (formula-api) | ADD COLUMN account_api_key_id UUID REFERENCES api_keys | Link calculators to API keys for gateway auth |

# 12. Migration Strategy: Zero Downtime

## 12.1 Principle: Proxy-First, Then Cutover

Every migration follows the same pattern to ensure zero downtime:

- Proxy: Directus continues serving the old endpoint but proxies requests to the new service

- Verify: Run both old and new in parallel. Compare responses (like ENGINE=both in formula-api)

- Cutover: Gateway routes directly to new service. Directus proxy removed.

- Cleanup: Remove old code from Directus extensions

## 12.2 AI Chat Migration (Example)

| Step | State | Client Sees | Risk |
| --- | --- | --- | --- |
| 1. Deploy bl-ai-api alongside Directus | Both running, bl-ai-api idle | No change (still hits Directus) | None |
| 2. Directus AI hook proxies to bl-ai-api | Directus → bl-ai-api | Same URL, faster responses | Low (proxy failure = fallback to local) |
| 3. Verify: compare responses for 1 week | Shadow mode | No change | None |
| 4. Gateway routes /v1/ai/* to bl-ai-api | Direct routing | New URL with API key auth | Medium (requires client update) |
| 5. Remove AI hook from Directus | bl-ai-api only | Full migration complete | None |

# 13. Timeline Summary

| Phase | Weeks | Calendar (from start) | Key Deliverable | Team |
| --- | --- | --- | --- | --- |
| 0: Foundation Fixes | 1-2 | Weeks 1-2 | HNSW index, BullMQ, version hashing | 1 dev |
| 1: bl-ai-api Extraction | 3-6 | Weeks 3-6 | Standalone AI service with worker pool + budget | 1-2 devs |
| 2: bl-gateway | 7-10 | Weeks 7-10 | Go API gateway with unified auth | 1 dev (Go) |
| 3: Public AI API | 11-14 | Weeks 11-14 | Public AI endpoints, MCP, SDK | 1-2 devs |
| 4: Flow as AI Backend | 15-20 | Weeks 15-20 | Flow-based KB ingestion, search, tool execution | 1-2 devs |
| 5: Hardening | 21-24 | Weeks 21-24 | OpenTelemetry, load tests, security audit | 1-2 devs |

Total elapsed time: ~24 weeks (6 months) with a team of 1-2 developers. Phases can overlap: Phase 2 (gateway) can start before Phase 1 is fully complete, since they are independent services. With 2 parallel developers, total wall time reduces to ~16-18 weeks.

# 14. Success Criteria

| Metric | Current | Target (Post-Phase 5) | Measurement |
| --- | --- | --- | --- |
| AI chat concurrent users | ~100 | 1,000+ | k6 load test: sustained 1K SSE streams |
| KB search latency (p95) | ~200ms (B-tree) | <50ms (HNSW) | PostgreSQL query log analysis |
| KB total chunks | ~50K before degradation | 5M+ with <100ms search | Production monitoring |
| Embedding cost | $0.02/M tokens (OpenAI) | $0 (local ONNX) | Monthly API billing |
| Service crash isolation | AI crash → Directus down | AI crash → only AI affected | Chaos testing (kill bl-ai-api) |
| Deployment independence | AI change requires CMS restart | Each service deploys independently | Coolify deploy logs |
| API key auth | Per-calculator tokens (fragmented) | Unified account API keys | Gateway auth logs |
| Cost control | Token tracking only | 5-layer budget enforcement | Budget exceeded → 429 test |
| End-to-end latency visibility | Basic logs | OpenTelemetry traces across all services | Grafana Tempo dashboard |
| Infrastructure cost | €31/mo | €57/mo for 10x capacity | Hetzner billing |

# 15. Risks and Mitigations

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Go expertise gap | Gateway delays | Medium | Go gateway is simple (proxy + auth). Plenty of reference implementations. Consider hiring Go consultant for initial scaffold. |
| Migration data loss | Lost conversations/KB | Low | Proxy-first pattern ensures both systems run in parallel. No data migration needed (shared PostgreSQL). |
| Performance regression during migration | Slower AI responses | Low | Shadow mode testing (run both, compare). Rollback by switching proxy back to Directus. |
| Scope creep in flow visual editor | Phase 4 delays | Medium | Phase 4 is independent. AI API works without flows. Flows add value but aren’t blocking. |
| Anthropic SDK changes | bl-ai-api breakage | Low | Pin SDK version. Monthly update cycle. The API is stable. |
| Coolify limitations for multi-server | Deployment complexity | Low | Coolify supports multi-server via agents. Already proven with current 3-server setup. |
| Redis single point of failure | All services degraded | Medium | Phase 5: Redis Sentinel on S3. In-memory fallback in all services (already in formula-api). |

# Appendix A: Service Port Map

| Service | Internal Port | Public Path (via Gateway) | Protocol |
| --- | --- | --- | --- |
| bl-gateway | 443 (public), 8080 (admin) | — (is the gateway) | HTTPS / HTTP |
| bl-cms | 8055 | /admin/* | HTTP |
| bl-ai-api | 3200 | /v1/ai/* | HTTP + SSE |
| bl-formula-api | 3000 | /v1/calc/*, /v1/mcp/calc/* | HTTP |
| bl-flow-trigger | 3100 | /v1/flows/webhook/* | HTTP |
| bl-flow-worker | — (no HTTP) | — | Redis Streams consumer |
| PostgreSQL | 5432 | — (private only) | PostgreSQL wire |
| Redis | 6379 | — (private only) | RESP |

# Appendix B: Environment Variables (New Services)

### bl-gateway

| Variable | Default | Purpose |
| --- | --- | --- |
| PORT | 443 | Public HTTPS port |
| ADMIN_PORT | 8080 | Internal admin/health port |
| REDIS_URL | — (required) | For API key cache, rate limiting |
| DATABASE_URL | — (required) | For API key fallback lookup |
| AI_API_URL | http://10.0.0.40:3200 | bl-ai-api backend |
| FORMULA_API_URL | http://10.0.0.30:3000 | bl-formula-api backend |
| FLOW_TRIGGER_URL | http://10.0.0.30:3100 | bl-flow-trigger backend |
| CMS_URL | http://10.0.0.10:8055 | bl-cms backend |
| LOG_LEVEL | info | Structured logging level |
| RATE_LIMIT_DEFAULT_RPS | 100 | Default per-key RPS |

### bl-ai-api

| Variable | Default | Purpose |
| --- | --- | --- |
| PORT | 3200 | HTTP port |
| REDIS_URL | — (required) | Cache, rate limits, job queues |
| DATABASE_URL | — (required) | Conversations, KB data, cost tracking |
| ANTHROPIC_API_KEY | — (required) | Claude API access |
| CHAT_POOL_SIZE | 4 | Worker threads for LLM streaming |
| EMBED_POOL_SIZE | 2 | Worker threads for embedding |
| INGEST_POOL_SIZE | 2 | BullMQ workers for KB ingestion |
| MAX_QUEUE_DEPTH | 256 | Backpressure limit (503 when full) |
| EMBEDDING_PROVIDER | local | local (ONNX) or openai |
| EMBEDDING_MODEL | BAAI/bge-small-en-v1.5 | Local ONNX model name |
| DAILY_BUDGET_USD | 10.00 | Default daily per-account limit |
| MONTHLY_BUDGET_USD | 100.00 | Default monthly per-account limit |
| GLOBAL_BUDGET_USD | 500.00 | Platform-wide daily limit |
| CACHE_MAX_ITEMS | 10000 | L1 LRU cache size |
| CACHE_REDIS_TTL_S | 3600 | L2 Redis cache TTL |

Document prepared by: Architecture Analysis Agent

Date: March 20, 2026 — Version 1.0

Classification: Confidential — Internal Use Only